## Sheet2
Test Estimation Document for Google Search Engine Project Name: Google Search Engine Project Manager: [Project Manager's Name] Test Manager: [Test Manager's Name] Project Start Date: [ 09/11/2023] Project End Date: [ 01/02/2024]
Assumptions Availability of Resources: It is assumed that the necessary resources, including testers and specialists, will be available as required. Documentation: It is assumed that project documentation, requirements, and test data will be provided as needed. Test Data: Test data required for testing will be available when needed. Stability: The test environments will remain stable during the testing phases. Approval for Production Release: Test closure assumes that all test phases are completed, and approval for production release is granted. Tools Availability: Testing tools and software required for testing are available and functional. Test Scenarios: Usability testing assumes that test scenarios and user profiles are defined. Dependencies: No significant external dependencies are expected to delay testing.
Test Phases and Estimates
Test Phase | Description | Estimated Effort (in hours) | Resources Required | Start Date | End Date
1. Test Planning | Define test objectives, scope, and strategy. | 40 | Abhay(Test Lead), Suresh (Test Analyst) | 2023-09-11 | 2023-09-16
2. Test Case Design | Create test cases, test data, and test scripts. | 40 | Suresh (Test Analyst) | 2023-09-17 | 2023-09-27
3. Test Environment Setup | Prepare the test environment, including hardware and software. | 40 | Dinesh (Environment Specialist) | 2023-09-28 | 2023-10-05
4. Functional Testing | Execute functional test cases. | 120 | Abhay (Test Lead), Suresh (Test Analyst) | 2023-10-06 | 2023-10-27
5. Compatibility Testing | Test on various browsers and devices. | 40 | Suresh (Test Analyst) | 2023-10-28 | 2023-11-04
6. Mobile Responsiveness Testing | Ensure mobile compatibility. | 40 | Suresh (Mobile Testing Specialist) | 2023-11-05 | 2023-11-12
7. Security Testing | Assess security vulnerabilities. | 80 | Alok (Security Testing Specialist) | 2023-11-13 | 2023-11-28
8. Performance Testing | Measure system performance under load. | 80 | Rishu (Performance Testing Specialist) | 2023-11-29 | 2023-12-13
9. Usability Testing | Gather user feedback on the user interface. | 40 | Mark (Usability Testing Specialist), User Participants | 2023-12-14 | 2023-12-21
10. Test Reporting | Document and communicate test results. | 40 | Abhay (Test Lead), Susan (Test Analyst) | 2023-12-22 | 2023-12-29
11. Test Closure | Formalize the test closure process. | 20 | Abhay (Test Lead) | 2023-12-30 | 2024-01-02
Total Effort |  | 580